## Dashboard
Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters.
Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters. | Executive rollup for PROD, PT, and UAT load balancer implementation across 51 Kafka clusters.
Metric | Value |  | Environment | Clusters | Completed | Blocked | Avg Complete | MRC Clusters
Total Clusters | 51 |  | PROD | 17 | 0 | 0 | 0% | 6
Completed | 0 |  | PT | 17 | 0 | 0 | 0% | 6
In Progress | 0 |  | UAT | 17 | 0 | 0 | 0% | 6
Blocked | 0 |  | Total | 51 | 0 | 0 | 0% | 18
Overall Complete | 0%
Status | Count | Share |  | Next Action Queue | Environment | Cluster | Next Thing To Do
Not Started | 51 | 100% |  | 1 | PROD | prod-kafka-01 | Confirm LB IP allocation and DNS naming standard
Planned | 0 | 0% |  | 2
IP Reserved | 0 | 0% |  | 3
DNS Created | 0 | 0% |  | 4
LB Configured | 0 | 0% |  | 5
Validation | 0 | 0% |  | 6
Completed | 0 | 0%
Blocked | 0 | 0%

## Cluster Tracker
Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action.
Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action. | Track cluster load balancer IP/DNS, MRC VAP/WIP details, build milestones, current status, percent complete, and next action.
Environment | Cluster Name | Cluster Type | Service | LB IP Address | LB DNS Name | VAP Name | VAP IP Address | VAP DNS Name | WIP 1 Name | WIP 1 IP Address | WIP 1 DNS Name | WIP 2 Name | WIP 2 IP Address | WIP 2 DNS Name | IP Reserved | DNS Created | LB Configured | Health Check Passed | Cutover Validated | Progress % | Status | Owner | Target Date | Next Thing To Do | Comments
PROD | prod-kafka-01 | Normal | Kafka Bootstrap |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-02 | Normal | Kafka Broker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-03 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-04 | MRC | Kafka Connect |  |  | prod-vap-04 |  |  | prod-wip-a-04 |  |  | prod-wip-b-04 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-05 | Normal | KSQL |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-06 | Normal | MirrorMaker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-07 | MRC | Admin/API |  |  | prod-vap-07 |  |  | prod-wip-a-07 |  |  | prod-wip-b-07 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-08 | MRC | Kafka Bootstrap |  |  | prod-vap-08 |  |  | prod-wip-a-08 |  |  | prod-wip-b-08 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-09 | Normal | Kafka Broker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-10 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-11 | Normal | Kafka Connect |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-12 | MRC | KSQL |  |  | prod-vap-12 |  |  | prod-wip-a-12 |  |  | prod-wip-b-12 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-13 | Normal | MirrorMaker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-14 | MRC | Admin/API |  |  | prod-vap-14 |  |  | prod-wip-a-14 |  |  | prod-wip-b-14 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-15 | Normal | Kafka Bootstrap |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-16 | MRC | Kafka Broker |  |  | prod-vap-16 |  |  | prod-wip-a-16 |  |  | prod-wip-b-16 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PROD | prod-kafka-17 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-01 | Normal | Kafka Bootstrap |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-02 | Normal | Kafka Broker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-03 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-04 | MRC | Kafka Connect |  |  | pt-vap-04 |  |  | pt-wip-a-04 |  |  | pt-wip-b-04 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-05 | Normal | KSQL |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-06 | Normal | MirrorMaker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-07 | MRC | Admin/API |  |  | pt-vap-07 |  |  | pt-wip-a-07 |  |  | pt-wip-b-07 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-08 | MRC | Kafka Bootstrap |  |  | pt-vap-08 |  |  | pt-wip-a-08 |  |  | pt-wip-b-08 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-09 | Normal | Kafka Broker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-10 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-11 | Normal | Kafka Connect |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-12 | MRC | KSQL |  |  | pt-vap-12 |  |  | pt-wip-a-12 |  |  | pt-wip-b-12 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-13 | Normal | MirrorMaker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-14 | MRC | Admin/API |  |  | pt-vap-14 |  |  | pt-wip-a-14 |  |  | pt-wip-b-14 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-15 | Normal | Kafka Bootstrap |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-16 | MRC | Kafka Broker |  |  | pt-vap-16 |  |  | pt-wip-a-16 |  |  | pt-wip-b-16 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
PT | pt-kafka-17 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-01 | Normal | Kafka Bootstrap |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-02 | Normal | Kafka Broker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-03 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-04 | MRC | Kafka Connect |  |  | uat-vap-04 |  |  | uat-wip-a-04 |  |  | uat-wip-b-04 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-05 | Normal | KSQL |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-06 | Normal | MirrorMaker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-07 | MRC | Admin/API |  |  | uat-vap-07 |  |  | uat-wip-a-07 |  |  | uat-wip-b-07 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-08 | MRC | Kafka Bootstrap |  |  | uat-vap-08 |  |  | uat-wip-a-08 |  |  | uat-wip-b-08 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-09 | Normal | Kafka Broker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-10 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-11 | Normal | Kafka Connect |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-12 | MRC | KSQL |  |  | uat-vap-12 |  |  | uat-wip-a-12 |  |  | uat-wip-b-12 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-13 | Normal | MirrorMaker |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-14 | MRC | Admin/API |  |  | uat-vap-14 |  |  | uat-wip-a-14 |  |  | uat-wip-b-14 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-15 | Normal | Kafka Bootstrap |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-16 | MRC | Kafka Broker |  |  | uat-vap-16 |  |  | uat-wip-a-16 |  |  | uat-wip-b-16 |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard
UAT | uat-kafka-17 | Normal | Schema Registry |  |  | N/A |  |  | N/A |  |  | N/A |  |  | No | No | No | No | No | 0% | Not Started |  |  | Confirm LB IP allocation and DNS naming standard

## Lists
Status | Cluster Type | Service | Yes/No/N/A | Environment
Not Started | Normal | Kafka Bootstrap | No | PROD
Planned | MRC | Kafka Broker | Yes | PT
IP Reserved |  | Schema Registry | N/A | UAT
DNS Created |  | Kafka Connect
LB Configured |  | KSQL
Validation |  | MirrorMaker
Completed |  | Admin/API
Blocked